## Sheet1
Team 1, Project 2
Product Backlog
Priority | Feature | Estimated Complexity (out of 10 with 10 being high complexity and 1 being low complexity | Estimated time required for completion
High
| Implement date constraints | 4 | 1-2 hr
| Change date display to MM/DD/YYYY | 3 | 30 min
| Changing order of time slots | 5 | 1.5 hr
| Task list creation (only possible by event creator) | 7 | 3-4 hr
| Allowing attendees to sign up for tasks | 6 | 1-2 hr
| Scheduling over multiple days | 8 | 3-4 hr
| Allowing to copy times to a different day to avoid re-entering | 6 | 1-2 hr
| Modify event creator's view to see who is attending when | 5 | 1-2 hr
| Modify event creator's view to see who is bringing what item from task list | 5 | 1-2 hr
| Event attendees modification with task list and new time slots | 6 | 2-3 hr
| Making sure multiple attendees cannot sign up for the same task | 4 | 30 min
Medium
| Scheduling interface improvements | 6 | 1 hr
| Missing second "0" on ":00" times | 3 | 20 min
| Getting rid of "No Valid input" when choosing menu option | 3 | 20 min
Low
| 12/24 Time toggling to be taken out of separate menu option | 5 | 30 min
| Refining View Events mode | 5 | 30 min
| Styling of menu | 3 | 30-40 min